## Risk_Matrix
Risk Matrix
1-2 Very Low
3-4 Low
4-9 - Medium
10-12 High
13-16 Very High
16< Extreme
Impact
Likelihood |  | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Severe
| 5 Almost Certain | 5 Medium | 10 High | 15 Very High | 20 Extreme | 25 Extreme
| 4 Likely | 4 Medium | 8 Medium | 12 High | 16 Very High | 20 Extreme
| 3 Possible | 3 Low | 6 Medium | 9 Medium | 12 High | 15 Very High
| 2 Unlikely | 2 Very Low | 4 Low | 6 Medium | 8 Medium | 10 High
| 1 Rare | 1 Very Low | 2 Very Low | 3 Low | 4 Medium | 5 Medium

## Risk Register
Assessment
Risk ID | Date Raised | Description | Asset Affected | Likelihood Rating | Impact Rating | Risk Score | Risk Action | Risk Treatment | Risk Owner | Status | Residual Risk | Notes
BKSP-001 | 2025-09-01 | SQL Injection vulnerability detected in Bookshop customer-facing e-commerce web application. Found in search functionality and login forms allowing unauthorized database access and data manipulation. | bookshop-db | 4 | 5 | 20 | Mitigate | Layered approach: 1. Implement parameterized queries, 2. Add input validation, 3. Apply output encoding, 4. Apply principle of least privilege to database user accounts | Security Team | In Progress |  | Discovered through manual and automated security assessments. Affects login.php, books.php, orders.php, admin/login.php. Prioritize mitigation.